## Sheet1
Start Date | Integrated Gym Management System | [5 empty] | Calendar Week-23 (2026) | [6 empty] | Calendar Week-24 (2026) | [6 empty] | Calendar Week-25 (2026) | [6 empty] | Calendar Week-26 (2026) | [6 empty] | Calendar Week-27 (2026) | [6 empty] | Calendar Week-28 (2026) | [6 empty] | Calendar Week-29 (2026) | [6 empty] | Calendar Week-30 (2026) | [6 empty] | Calendar Week-31 (2026) | [6 empty] | Calendar Week-32 (2026) | [6 empty] | Calendar Week-33 (2026)
2026-06-05 | [6 empty] | June | [29 empty] | July | [30 empty] | August
S.NO. | Activity | Duration | Plan Start | Plan End | Responsible | Predecessor | time axis 2026-06-01 to 2026-08-14
|  |  | Actual Start | Actual End | time axis 2026-06-01 to 2026-08-14
1 | Planning & Requirement Analysis | 14 | 2026-06-05 | 2026-06-18 | Hadia Nasir (PM) | - | bar: 2026-06-05 to 2026-06-18
|  | 14 | 2026-06-05 | 2026-06-18 | bar: 2026-06-05 to 2026-06-18
1.1 | Requirement Gathering & Interviews | 5 | 2026-06-05 | 2026-06-09 | Hadia Nasir (PM) | - | bar: 2026-06-05 to 2026-06-09
|  | 5 | 2026-06-05 | 2026-06-09 | bar: 2026-06-05 to 2026-06-09
1.1.1 | Interview Gym Owners & Admins | 2 | 2026-06-05 | 2026-06-06 | Hadia Nasir (PM) | - | bar: 2026-06-05 to 2026-06-06
|  | 2 | 2026-06-05 | 2026-06-06 | bar: 2026-06-05 to 2026-06-06
1.1.2 | Define Trainer & Member Expectations | 2 | 2026-06-08 | 2026-06-09 | Hadia Nasir (PM) | 1.1.1 | bar: 2026-06-08 to 2026-06-09
|  | 2 | 2026-06-08 | 2026-06-09 | bar: 2026-06-08 to 2026-06-09
1.2 | Feasibility Study & Payment Exploration | 4 | 2026-06-10 | 2026-06-13 | Haider Zaman (Developer) | 1.1 | bar: 2026-06-10 to 2026-06-13
|  | 4 | 2026-06-10 | 2026-06-13 | bar: 2026-06-10 to 2026-06-13
1.3 | Finalize Project Scope Document | 4 | 2026-06-15 | 2026-06-18 | Hadia Nasir (PM) | 1.2 | bar: 2026-06-15 to 2026-06-18
|  | 3 | 2026-06-16 | 2026-06-18 | bar: 2026-06-16 to 2026-06-18
1.4 | ◆ Milestone: Project Charter Approved |  |  |  | All Members | 1.3
2 | System & Interface Design Phase | 12 | 2026-06-19 | 2026-06-30 | Ahmad Khan (UI/UX) | 1 | bar: 2026-06-19 to 2026-06-30
|  | 12 | 2026-06-19 | 2026-06-30 | bar: 2026-06-19 to 2026-06-30
2.1 | Architectural Design & ER Diagram | 4 | 2026-06-19 | 2026-06-22 | Muneeb Akram (Backend) | 1.4 | bar: 2026-06-19 to 2026-06-22
|  | 4 | 2026-06-19 | 2026-06-22 | bar: 2026-06-19 to 2026-06-22
2.2 | UI/UX Wireframing & Prototyping | 8 | 2026-06-23 | 2026-06-30 | Ahmad Khan (UI/UX) | 2.1 | bar: 2026-06-23 to 2026-06-30
|  | 8 | 2026-06-23 | 2026-06-30 | bar: 2026-06-23 to 2026-06-30
2.2.1 | Design Gym Admin Dashboard Mockup | 3 | 2026-06-23 | 2026-06-25 | Ahmad Khan (UI/UX) | 2.1 | bar: 2026-06-23 to 2026-06-25
|  | 3 | 2026-06-23 | 2026-06-25 | bar: 2026-06-23 to 2026-06-25
2.2.2 | Design Trainer & Member Interfaces | 2 | 2026-06-26 | 2026-06-27 | Ahmad Khan (UI/UX) | 2.2.1 | bar: 2026-06-26 to 2026-06-27
|  | 2 | 2026-06-26 | 2026-06-27 | bar: 2026-06-26 to 2026-06-27
2.2.3 | Design Checkout / Payment Portal | 2 | 2026-06-29 | 2026-06-30 | Ahmad Khan (UI/UX) | 2.2.2 | bar: 2026-06-29 to 2026-06-30
|  | 2 | 2026-06-29 | 2026-06-30 | bar: 2026-06-29 to 2026-06-30
2.3 | ◆ Milestone: UI Wireframes Frozen |  |  |  | All Members | 2.2
3 | Software Development Phase (Coding) | 30 | 2026-07-01 | 2026-07-30 | Development Team | 2 | bar: 2026-07-01 to 2026-07-30
|  | 30 | 2026-07-01 | 2026-07-30 | bar: 2026-07-01 to 2026-07-30
3.1 | Core Database Setup & Configuration | 3 | 2026-07-01 | 2026-07-03 | Muneeb Akram (Backend) | 2.3 | bar: 2026-07-01 to 2026-07-03
|  | 3 | 2026-07-01 | 2026-07-03 | bar: 2026-07-01 to 2026-07-03
3.2 | User Authentication Secure Registration | 6 | 2026-07-04 | 2026-07-09 | Haider Zaman (Full-Stack) | 3.1 | bar: 2026-07-04 to 2026-07-09
|  | 6 | 2026-07-04 | 2026-07-09 | bar: 2026-07-04 to 2026-07-09
3.2.1 | Implement Verified Sign-up Process | 3 | 2026-07-04 | 2026-07-06 | Haider Zaman (Full-Stack) | 3.1 | bar: 2026-07-04 to 2026-07-06
|  | 3 | 2026-07-04 | 2026-07-06 | bar: 2026-07-04 to 2026-07-06
3.2.2 | Configure Role-Based Dashboard Access | 3 | 2026-07-07 | 2026-07-09 | Muneeb Akram (Backend) | 3.2.1 | bar: 2026-07-07 to 2026-07-09
|  | 3 | 2026-07-07 | 2026-07-09 | bar: 2026-07-07 to 2026-07-09
3.3 | Gym Admin & Member Management Panel | 7 | 2026-07-10 | 2026-07-16 | Ahmad Khan (Frontend) | 3.2 | bar: 2026-07-10 to 2026-07-16
|  | 7 | 2026-07-10 | 2026-07-16 | bar: 2026-07-10 to 2026-07-16
3.4 | Workout & Exercise Assignment Module | 5 | 2026-07-17 | 2026-07-21 | Muneeb Akram (Backend) | 3.3 | bar: 2026-07-17 to 2026-07-21
|  | 5 | 2026-07-17 | 2026-07-21 | bar: 2026-07-17 to 2026-07-21
3.5 | Billing & Online Payment Integration | 9 | 2026-07-22 | 2026-07-30 | Haider Zaman (Full-Stack) | 3.4 | bar: 2026-07-22 to 2026-07-30
|  | 9 | 2026-07-22 | 2026-07-30 | bar: 2026-07-22 to 2026-07-30
3.5.1 | Integrate JazzCash API & Bank Uploads | 5 | 2026-07-22 | 2026-07-26 | Haider Zaman (Full-Stack) | 3.4 | bar: 2026-07-22 to 2026-07-26
|  | 6 | 2026-07-22 | 2026-07-27 | bar: 2026-07-22 to 2026-07-27
3.5.2 | Develop Automated 7-Day Fee Reminders | 3 | 2026-07-28 | 2026-07-30 | Muneeb Akram (Backend) | 3.5.1 | bar: 2026-07-28 to 2026-07-30
|  | 3 | 2026-07-28 | 2026-07-30 | bar: 2026-07-28 to 2026-07-30
4 | Testing & Quality Assurance Phase | 10 | 2026-07-31 | 2026-08-09 | Muneeb Akram (Backend) | 3 | bar: 2026-07-31 to 2026-08-09
|  | 10 | 2026-07-31 | 2026-08-09 | bar: 2026-07-31 to 2026-08-09
4.1 | Write Comprehensive Test Cases | 3 | 2026-07-31 | 2026-08-02 | Hadia Nasir (QA) | 3.5 | bar: 2026-07-31 to 2026-08-02
|  | 3 | 2026-07-31 | 2026-08-02 | bar: 2026-07-31 to 2026-08-02
4.2 | Unit and Integration Testing | 4 | 2026-08-03 | 2026-08-06 | Hadia Nasir (QA) | 4.1 | bar: 2026-08-03 to 2026-08-06
|  | 4 | 2026-08-03 | 2026-08-06 | bar: 2026-08-03 to 2026-08-06
4.3 | Payment Gateways Verification Testing | 3 | 2026-08-07 | 2026-08-09 | Hadia Nasir (QA) | 4.2 | bar: 2026-08-07 to 2026-08-09
|  | 3 | 2026-08-07 | 2026-08-09 | bar: 2026-08-07 to 2026-08-09
5 | Deployment & Closure Phase | 5 | 2026-08-10 | 2026-08-14 | Hadia Nasir (PM) | 4 | bar: 2026-08-10 to 2026-08-14
|  | 5 | 2026-08-10 | 2026-08-14 | bar: 2026-08-10 to 2026-08-14
5.1 | Server Hosting Setup & Final Deployment | 3 | 2026-08-10 | 2026-08-12 | Haider Zaman (Full-Stack) | 1.3 | bar: 2026-08-10 to 2026-08-12
|  | 3 | 2026-08-10 | 2026-08-12 | bar: 2026-08-10 to 2026-08-12
5.2 | User Documentation & Admin Training | 2 | 2026-08-13 | 2026-08-14 | Ahmad Khan (Frontend) | 5.1 | bar: 2026-08-13 to 2026-08-14
|  | 2 | 2026-08-13 | 2026-08-14 | bar: 2026-08-13 to 2026-08-14
5.3 | ◆ Milestone: System Live & Handed Over |  |  |  | All Mambers | 5.2