## Resource List
Resource ID | Resource Name | Type | Max Units | Std Rate | Overallocated
R01 | Hadia Nasir (PM) | Work | 100% | $5000.00/hr | No
R02 | Haider Zaman (Developer) | Work | 100% | $2000.00/hr | No
R03 | All Members | Work | 100% | $1000.00/hr | No
R04 | Ahmad Khan (UI/UX) | Work | 100% | $3000.00/hr | No
R05 | Muneeb Akram (Backend) | Work | 100% | $3000.00/hr | No
R06 | Development Team | Work | 100% | $6000.00/hr | No
R07 | Haider Zaman (Full-Stack) | Work | 50% | $7000.00/hr | Yes
R08 | Ahmad Khan (Frontend) | Work | 100% | $1000.00/hr | No
R09 | Hadia Nasir (QA) | Work | 100% | $4000.00/hr | No

## Assigned Tasks
Task ID | Task Name | Duration | Start Date | End Date | Assigned Resource
1 | Planning & Requirement Analysis | 19 days | 2026-06-08 | 2026-07-02 | Hadia Nasir (PM)
1.1 | Requirement Gathering & Interviews | 5 days | 2026-06-08 | 2026-06-12 | Hadia Nasir (PM)
1.2 | Interview Gym Owners & Admins | 2 days | 2026-06-15 | 2026-06-16 | Hadia Nasir (PM)
1.3 | Define Trainer & Member Expectations | 3 days | 2026-06-17 | 2026-06-19 | Hadia Nasir (PM)
1.4 | Feasibility Study & Payment Exploration | 4 days | 2026-06-22 | 2026-06-25 | Haider Zaman (Developer)
1.5 | Finalize Project Scope Document | 5 days | 2026-06-26 | 2026-07-02 | Hadia Nasir (PM)
1.6 | Milestone: Project Charter Approved | 0 days | 2026-07-02 | 2026-07-02 | All Members
2 | System & Interface Design Phase | 20 days | 2026-07-03 | 2026-07-30 | Ahmad Khan (UI/UX)
2.1 | Architectural Design & ER Diagram | 4 days | 2026-07-03 | 2026-07-08 | Muneeb Akram (Backend)
2.2 | UI/UX Wireframing & Prototyping | 8 days | 2026-07-09 | 2026-07-20 | Ahmad Khan (UI/UX)
2.3 | Design Gym Admin Dashboard Mockup | 3 days | 2026-07-21 | 2026-07-23 | Ahmad Khan (UI/UX)
2.4 | Design Trainer & Member Interfaces | 3 days | 2026-07-24 | 2026-07-28 | Ahmad Khan (UI/UX)
2.5 | Design Checkout / Payment Portal | 2 days | 2026-07-29 | 2026-07-30 | Ahmad Khan (UI/UX)
2.6 | Milestone: UI Wireframes Frozen | 0 days | 2026-07-30 | 2026-07-30 | All Members
3 | Software Development Phase (Coding) | 44 days | 2026-07-31 | 2026-09-30 | Development Team
3.1 | Core Database Setup & Configuration | 3 days | 2026-07-31 | 2026-08-04 | Muneeb Akram (Backend)
3.2 | User Authentication Secure Registration | 6 days | 2026-08-05 | 2026-08-12 | Haider Zaman (Full-Stack)
3.3 | Implement Verified Sign-up Process | 3 days | 2026-08-13 | 2026-08-17 | Haider Zaman (Full-Stack)
3.4 | Configure Role-Based Dashboard Access | 3 days | 2026-08-18 | 2026-08-20 | Muneeb Akram (Backend)
3.5 | Gym Admin & Member Management Panel | 7 days | 2026-08-21 | 2026-08-31 | Ahmad Khan (Frontend)
3.6 | Workout & Exercise Assignment Module | 5 days | 2026-09-01 | 2026-09-07 | Muneeb Akram (Backend)
3.7 | Billing & Online Payment Integration | 9 days | 2026-09-08 | 2026-09-18 | Haider Zaman (Full-Stack)
3.8 | Integrate JazzCash API & Bank Uploads | 5 days | 2026-09-21 | 2026-09-25 | Haider Zaman (Full-Stack)
3.9 | Develop Automated 7-Day Fee Reminders | 3 days | 2026-09-28 | 2026-09-30 | Haider Zaman (Full-Stack)
4 | Testing & Quality Assurance Phase | 20 days | 2026-10-01 | 2026-10-28 | Hadia Nasir (QA)
4.1 | Write Comprehensive Test Cases | 3 days | 2026-10-01 | 2026-10-05 | Hadia Nasir (QA)
4.2 | Unit and Integration Testing | 4 days | 2026-10-06 | 2026-10-09 | Hadia Nasir (PM)
4.3 | Payment Gateways Verification Testing | 3 days | 2026-10-12 | 2026-10-14 | Hadia Nasir (QA)
4.4 | Deployment & Closure Phase | 5 days | 2026-10-15 | 2026-10-21 | Hadia Nasir (PM)
4.5 | Server Hosting Setup & Final Deployment | 3 days | 2026-10-22 | 2026-10-26 | Haider Zaman (Full-Stack)
4.6 | User Documentation & Admin Training | 2 days | 2026-10-27 | 2026-10-28 | Ahmad Khan (Frontend)
4.7 | Milestone: System Live & Handed Over | 0 days | 2026-10-28 | 2026-10-28 | All Members

## Working Hours
Resource Name | Role | Total Tasks Assigned | Total Working Days | Hours/Day | Total Hours
Hadia Nasir (PM) | Project Manager | 6 | 24 | 8 | 192
Hadia Nasir (QA) | QA Lead | 2 | 6 | 8 | 48
Ahmad Khan (UI/UX) | UI/UX Designer | 4 | 16 | 8 | 128
Ahmad Khan (Frontend) | Frontend Developer | 2 | 9 | 8 | 72
Muneeb Akram (Backend) | Backend Developer | 5 | 15 | 8 | 120
Haider Zaman (Developer) | Developer | 1 | 4 | 8 | 32
Haider Zaman (Full-Stack) | Full-Stack Dev | 6 | 29 | 4 | 116
Development Team | Mixed | 1 | 44 | 8 | 352
All Members | Milestone | 3 | 0 | 0 | 0

## Overallocation Details
Resource Name | Overallocated | Max Units | Conflicting Tasks | Overlap Period | Reason
Ahmad Khan (UI/UX) | No | 100% | N/A | N/A | Max Units increased to 100%. No overallocation.
Haider Zaman (Full-Stack) | Yes | 50% | Task 3.2 + Task 3.3 + Task 3.7 + Task 3.8 + Task 3.9 + Task 4.5 | 05-Aug-26 to 26-Oct-26 | Haider Zaman has only 50% availability but assigned to 6 tasks across development and deployment phases. At 50% max units, workload exceeds his available capacity.
Hadia Nasir (PM) | No | 100% | N/A | N/A | Tasks are scheduled sequentially. No overallocation detected.
Muneeb Akram (Backend) | No | 100% | N/A | N/A | Tasks are scheduled sequentially. No overallocation detected.

## Solution Applied
Resource Name | Overallocated Task(s) | Resolution Method | Action Taken
Haider Zaman (Full-Stack) | Task 3.2 + 3.3 + 3.7 + 3.8 + 3.9 + 4.5 — 50% Max Units causing overallocation | Manual Resource Allocation | The Resource Sheet shows that the resource has a maximum allocation limit of 50% (Max Units). However, the Gantt Chart identified an overallocation because the assigned workload exceeded this limit. The conflict was resolved using the Manual Resource Allocation technique by reducing the workload to 50%.