## Sheet1
1 day = 8 hours
Task | Days | Standered Hours | Hours(Day*8)
Planning & Requirement Analysis | 19 | 8 | 152
System & Interface Design Phase | 20 | 8 | 160
Software Development Phase (Coding) | 44 | 8 | 352
Testing & Quality Assurance Phase | 20 | 8 | 160
A- Task Cost Estimation
| Task Name | Estimated Hours | Rate Per Hours($) | Total Cost
| Planning & Requirement Analysis | 152 | 50 | 7600
| System & Interface Design Phase | 136 | 60 | 8160
| Software Development Phase (Coding) | 248 | 70 | 17360
| Testing & Quality Assurance Phase | 148 | 75 | 11100
| Total Cost | 684 |  | 44220
B- Resource Cost Estimation
| Resource Name | Hours Worked | Hours | Total Hours Worked | Std/Rate | Total Pay
| Hadia Nasir (PM) | 24 | 8 | 192 | 5000 | 960000
| Haider Zaman (Developer) | 4 | 8 | 32 | 2000 | 64000
| Ahmad Khan (UI/UX) | 16 | 8 | 128 | 3000 | 384000
| Muneeb Akram (Backend) | 15 | 8 | 120 | 3000 | 360000
| Development Team | 3.5 | 8 | 28 | 6000 | 168000
| Haider Zaman (Full-Stack) | 14.5 | 8 | 116 | 7000 | 812000
| Ahmad Khan (Frontend) | 5.5 | 8 | 44 | 1000 | 44000
| Hadia Nasir (QA) | 6 | 8 | 48 | 4000 | 192000
| Total Cost |  |  |  |  | 2984000
| Total Task Estimation | 44220
| Total Resource Cost Estimation | 2984000
| Total Project Budget | 3028220